## Instructions (hidden)
Construction Budget Submission Form Instructions
Welcome to Lima One Capital!
The Construction Budget Submission Form is an important tool for allowing underwriting analysts, Construction Management Specialists, and inspectors to better understand your vision and plans for your renovation project. This form allows you the opportunity to tell your story of what you envision and how we can help you.
As you complete this worksheet, we encourage you to use the description fields to be as detailed, accurate and thorough, as possible. This will help expedite the underwriting process including your budget review inspection, which in turn helps your loan close more quickly.
The 'Example' worksheet provides a sample of what a completed Construction Budget Submission Form should look like. We encourage you to take some time to review it before proceeding with your own project on the worksheet entitled 'Construction Budget'.
Should you need help understanding or completing the worksheet, you may call 800-390-4212, M-F 9 AM-6 PM EST.
Before you start, we would encourage you to contact your local government regarding plans and permits you may need. In addition, it is beneficial to consult with a licensed general contractor and/or tradespeople for an estimate of costs and a quote.
Keep in mind that your Lima One Capital loan will be on a reimbursement model. This means that you are to use your own reserve funds to begin your project. You then request draws for expenditures as you go. Please keep this in mind as you budget and schedule work.
Lima One Capital
Construction Management Team

## Example (hidden)
Construction Budget Submission Form
Version | 4.4
Step 1: Fill out a description of the entire construction project.
Status: Initial Budget
Scope of Work: |  | Start Date: | 2019-01-01 | Total Budget:
This property is located in the Greenville, SC area and will be a complete gut and flip. We will be putting in new drywall, hardwood flooring, tile in the kitchen, and carpet in the bedrooms. We will be putting in all new mid-grade fixtures in the bathroom. We will be painting the exterior of the property, putting in new fencing, and putting in new sod. |  | Estimated Completion Date: | 2019-07-01 | 71292
|  | Expected Draws: | 5
|  |  | Current | Projected
|  | Total Square Feet: | 2200 | 2200
|  | Rooms/Units: | 10 | 10
|  | Bedrooms: | 3 | 3
|  | Bathrooms: | 2 | 2
|  | Kitchens: | 1 | 1
Property Address: | 123 Main St, Greenville, SC 29605
Step 2: Fill in each line item with the description of the construction cost, the amount, the estimated date of completion, and the draw item name (if necessary).
Lima One Capital Budget Review
Item Number | Category / Draw Item | Description | Amount | Estimated Completion Date |  | Recommended Budget | Comments
Soft Costs
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
Column1: 1000-2; Soft Costs Column2: Temp Gas*; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
Column1: 1000-3; Soft Costs Column2: Temp Power* | #REF! | #REF!
Column1: 1000-4; Soft Costs Column2: Temp Toilet | #REF! | #REF!
Column1: 1000-5; Soft Costs Column2: Architecutral Fees | #REF! | #REF!
Column1: 1000-6; Soft Costs Column2: Engineering Fees | #REF! | #REF!
1000-7 | Building Permit* | Plumbing, electrical, Framing, HVAC | 1200 | 2019-09-01 | 1200 | #REF! | #REF!
Column1: 1000-8; Soft Costs Column2: Impact Fees | #REF! | #REF!
Column1: 1000-9; Soft Costs Column2: Survey | #REF! | #REF!
Column1: 1000-10; Soft Costs Column2: Survey/Drawings/Plans* | #REF! | #REF!
Column1: 1000-11; Soft Costs Column2: Erosion Fence | #REF! | #REF!
Column1: 1000-12; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 1000-13; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Soft Costs; Soft Costs Column4: 1200; Soft Costs Column6: 1200 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Demolition- Trashout | #REF! | #REF!
2000-1 | Demolition* | Gut the entire home | 2500 | 2019-09-18 | 2500 | #REF! | #REF!
Column1: 2000-2; Soft Costs Column2: Trashout | #REF! | #REF!
2000-3 | Dumpster | 4 30 yard dumpsters | 2000 | 2019-09-15 | 2000 | #REF! | #REF!
Column1: 2000-4; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 2000-5; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Trashout; Soft Costs Column4: 4500; Soft Costs Column6: 4500 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Site Work | #REF! | #REF!
Column1: 3000-1; Soft Costs Column2: Grading*; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
Column1: 3000-2; Soft Costs Column2: Underground * | #REF! | #REF!
Column1: 3000-3; Soft Costs Column2: Conduit | #REF! | #REF!
3000-4 | Water Lines* | Replacing water lines | 3750 | 2019-11-01 | 3750 | #REF! | #REF!
Column1: 3000-5; Soft Costs Column2: Septic * | #REF! | #REF!
Column1: 3000-6; Soft Costs Column2: Sewer Lines* | #REF! | #REF!
Column1: 3000-7; Soft Costs Column2: Landscape | #REF! | #REF!
Column1: 3000-8; Soft Costs Column2: Fence | #REF! | #REF!
Column1: 3000-9; Soft Costs Column2: Concrete | #REF! | #REF!
Column1: 3000-10; Soft Costs Column2: Asphalt | #REF! | #REF!
3000-11 | Hardscape | 7.5 ft wooden fencing in back yard | 1750 | 2019-12-01 | 1750 | #REF! | #REF!
3000-12 | Softscape | Sod the entire front and back yard | 2500 | 2020-01-15 | 2500 | #REF! | #REF!
Column1: 3000-13; Soft Costs Column2: Pool/Spa | #REF! | #REF!
Column1: 3000-14; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 3000-15; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Yard-Landscape; Soft Costs Column4: 8000; Soft Costs Column6: 8000 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Foundation | #REF! | #REF!
Column1: 4000-1; Soft Costs Column2: Footings*; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
Column1: 4000-2; Soft Costs Column2: PreTreat | #REF! | #REF!
Column1: 4000-3; Soft Costs Column2: Foundation - Post Tension Cables | #REF! | #REF!
Column1: 4000-4; Soft Costs Column2: Foundation * | #REF! | #REF!
Column1: 4000-5; Soft Costs Column2: Excavation* | #REF! | #REF!
Column1: 4000-6; Soft Costs Column2: Pour | #REF! | #REF!
Column1: 4000-7; Soft Costs Column2: Repair | #REF! | #REF!
Column1: 4000-8; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 4000-9; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Foundation; Soft Costs Column4: 0; Soft Costs Column6: 0 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Structure | #REF! | #REF!
Column1: 5000-1; Soft Costs Column2: Framing *; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
Column1: 5000-2; Soft Costs Column2: Roof Trusses | #REF! | #REF!
5000-3 | Windows | Replace all windows (16 New) | 5600 | 2019-10-15 | 5600 | #REF! | #REF!
Column1: 5000-4; Soft Costs Column2: Joist System | #REF! | #REF!
Column1: 5000-5; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 5000-6; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Structure; Soft Costs Column4: 5600; Soft Costs Column6: 5600 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Exterior | #REF! | #REF!
Column1: 6000-1; Soft Costs Column2: Roofing*; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
Column1: 6000-2; Soft Costs Column2: Flashing | #REF! | #REF!
6000-3 | Siding | Repair any damaged siding | 500 | 2020-01-20 | 500 | #REF! | #REF!
Column1: 6000-4; Soft Costs Column2: Stucco | #REF! | #REF!
Column1: 6000-5; Soft Costs Column2: Garage Door | #REF! | #REF!
Column1: 6000-6; Soft Costs Column2: Gutters/Soffit/Fascia | #REF! | #REF!
Column1: 6000-7; Soft Costs Column2: Solar | #REF! | #REF!
Column1: 6000-8; Soft Costs Column2: Deck | #REF! | #REF!
Column1: 6000-9; Soft Costs Column2: Driveway | #REF! | #REF!
Column1: 6000-10; Soft Costs Column2: Masonry Veneer | #REF! | #REF!
6000-11 | Painting - Exterior | Paint Exterior | 2250 | 2020-01-15 | 2250 | #REF! | #REF!
Column1: 6000-12; Soft Costs Column2: Porch | #REF! | #REF!
Column1: 6000-13; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 6000-14; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Exterior; Soft Costs Column4: 2750; Soft Costs Column6: 2750 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Systems | #REF! | #REF!
7000-1 | Rough HVAC* | Duct work installed | 2000 | 2019-12-15 | 2000 | #REF! | #REF!
7000-2 | Final HVAC | Unit installed | 2500 | 2019-12-15 | 2500 | #REF! | #REF!
Column1: 7000-3; Soft Costs Column2: Underslab Plumbing | #REF! | #REF!
7000-4 | Rough Plumbing* | All new plumbing in kitchen and bathrooms | 5500 | 2019-11-15 | 5500 | #REF! | #REF!
7000-5 | Plumbing - Fixtures | Bath Tub * 2 (With Shower); 2 toilets | 1650 | 2019-12-15 | 1650 | #REF! | #REF!
Column1: 7000-6; Soft Costs Column2: Fire Suppression | #REF! | #REF!
Column1: 7000-7; Soft Costs Column2: Underslab Electrical | #REF! | #REF!
7000-8 | Rough Electrical* | Run new wire throughout the house & new panel | 3500 | 2019-11-15 | 3500 | #REF! | #REF!
7000-9 | Electrical Fixtures | Canned lights; oulet covers; other lights | 1000 | 2020-02-01 | 1000 | #REF! | #REF!
Column1: 7000-10; Soft Costs Column2: Water Heater | #REF! | #REF!
Column1: 7000-11; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 7000-12; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Systems; Soft Costs Column4: 16150; Soft Costs Column6: 16150 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Interior | #REF! | #REF!
Column1: 8000-1; Soft Costs Column2: Fireplace; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
8000-2 | Insulation | New Insulation | 1000 | 2019-11-01 | 1000 | #REF! | #REF!
8000-3 | Drywall* | All rooms | 2750 | 2020-03-01 | 2750 | #REF! | #REF!
8000-4 | Paint-Interior | All Rooms | 4000 | 2020-04-15 | 4000 | #REF! | #REF!
Column1: 8000-5; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 8000-6; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Interior; Soft Costs Column4: 7750; Soft Costs Column6: 7750 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Finishes | #REF! | #REF!
Column1: 9000-1; Soft Costs Column2: Finish Carpentry; Soft Costs Column3: (Enter your description here) | #REF! | #REF!
9000-2 | Interior Doors | 16 4 panel doors | 2000 | 2020-02-15 | 2000 | #REF! | #REF!
9000-3 | Finish Hardware | Cabinet and door hardware | 300 | 2020-03-01 | 300 | #REF! | #REF!
9000-4 | Exterior Doors | Replace both exterior doors | 750 | 2020-10-15 | 750 | #REF! | #REF!
9000-5 | Mirrors | Vanity mirrors X2 | 225 | 2020-02-15 | 225 | #REF! | #REF!
Column1: 9000-6; Soft Costs Column2: Shower Doors | #REF! | #REF!
9000-7 | Cabinets | All new cherry cabinets | 6667 | 2020-03-01 | 6667 | #REF! | #REF!
9000-8 | Countertops | Granite | 2050 | 2020-03-15 | 2050 | #REF! | #REF!
9000-9 | Millwork | New Throughout House | 4195 | 2020-02-15 | 4195 | #REF! | #REF!
Column1: 9000-10; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 9000-11; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Finishes; Soft Costs Column4: 16187; Soft Costs Column6: 16187 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Flooring | #REF! | #REF!
10000-1 | Tile | Kitchen and bathrooms | 1725 | 2020-03-01 | 1725 | #REF! | #REF!
Column1: 10000-2; Soft Costs Column2: Marble | #REF! | #REF!
10000-3 | Wood Flooring | Hardwood throughout hallways and living room | 3330 | 2020-04-15 | 3330 | #REF! | #REF!
10000-4 | Carpet | All bedrooms | 1500 | 2020-03-15 | 1500 | #REF! | #REF!
Column1: 10000-5; Soft Costs Column2: Vinyl | #REF! | #REF!
Column1: 10000-6; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 10000-7; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Flooring; Soft Costs Column4: 6555; Soft Costs Column6: 6555 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Appliances | #REF! | #REF!
11000-1 | Range | (Enter your description here) | 500 | 2020-05-15 | 500 | #REF! | #REF!
Column1: 11000-2; Soft Costs Column2: Cooktop | #REF! | #REF!
11000-3 | Microwave |  | 350 | 2020-05-15 | 350 | #REF! | #REF!
11000-4 | Dishwasher |  | 500 | 2020-05-15 | 500 | #REF! | #REF!
11000-5 | Refrigerator |  | 750 | 2020-05-15 | 750 | #REF! | #REF!
Column1: 11000-6; Soft Costs Column2: Package | #REF! | #REF!
Column1: 11000-7; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 11000-8; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Soft Costs Column2: Total Appliances; Soft Costs Column4: 2100; Soft Costs Column6: 2100 | #REF! | #REF!
[6 empty] | #REF! | #REF!
Soft Costs Column2: Final - Misc | #REF! | #REF!
12000-1 | Final Clean | (Enter your description here) | 500 | 2020-05-15 | 500 | #REF! | #REF!
Column1: 12000-2; Soft Costs Column2: Staging | #REF! | #REF!
Column1: 12000-3; Soft Costs Column2: Contingency | #REF! | #REF!
Column1: 12000-4; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
Column1: 12000-5; Soft Costs Column2: (Enter your line item here) | #REF! | #REF!
| Total Misc. |  | 500 |  | 500
*THESE ITEMS REQUIRE PERMITS IN MOST JURISDICTIONS. BORROWERS ARE REQUIRED TO ADHERE TO ALL LOCAL LAWS, CODES, REGULATIONS AND REQUIREMENTS AS EXPRESSED IN YOUR LOAN DOCUMENTS.
p. 800-390-4212
Click for Internal Access
Re-Protect
Import
Example
Example
Example
Example
Example

## Construction Budget
v.
Construction Budget Submission Form
V | 5.1
Step 1: Fill out a description of the entire construction project.
Scope of Work: |  |  | Start Date: |  | Total Budget:
|  |  | Estimated Completion Date: |  | 0
Expected Draws:
|  |  |  | Current | Projected
Total Square Feet:
Rooms/Units:
Bedrooms:
Bathrooms:
Kitchens:
| Property Address: |  | Contractor: |  | Contact Name/Phone #: |  |  |  |  | =IF(AMT_Recommend1="","",AMT_Recommend1)
=IF(FR_Comments="","",FR_Comments)
Step 2: Fill in each line item with the description of the construction cost, the amount, the estimated date of completion, and the draw item name (if necessary). By filling out this budget template, you acknowledge and understand that draws operate on a reimbursement model, and funds will be released post-close for completed work only.
Lima One Capital Budget Review
| Item Number | Category / Draw Item | Description | Amount | Comments |  | Recommended Budget | Comments
Soft Costs
| Item Number | Category / Draw Item | Description | Amount | Estimated Completion Date | Column6
| 1000-1 | Gas* Service / meter set
| 1000-2 | Water Service/Meter Set
| 1000-3 | Temp Power*/service / meter set
| 1000-4 | Temp Toilet
| 1000-5 | Architecutral Fees
| 1000-6 | Engineering Fees
| 1000-7 | Building Permit*
| 1000-8 | Impact Fees
| 1000-9 | Survey/Drawings/Plans*
| 1000-10 | SWPP/ Erosion Control - Silt Fence
| 1000-11 | Temp Security / Privacy Fencing
| 1000-12 | (your description)
| 1000-13 | (your description)
|  | Total Soft Costs |  | 0 |  | 0
Demolition- Trashout
| 2000-1 | Demolition*
| 2000-2 | Trashout
| 2000-3 | Dumpster
| 2000-4 | HazMat Testing & Abatement
| 2000-5 | Mold Remediation
| 2000-6 | (your description)
| 2000-7 | (your description)
|  | Total Trashout |  | 0 |  | 0
Site Work
| 3000-1 | Grading*
| 3000-2 | Conduit / Electric Service
| 3000-3 | Water Lines*
| 3000-4 | Well
| 3000-5 | Septic *
| 3000-6 | Sewer Lines*
| 3000-7 | Flatwork -Conc Drive & Sidewalks
| 3000-8 | Asphalt
| 3000-9 | Pavers-Hardscape
| 3000-10 | Landscape (Package or Maintenance)
| 3000-11 | Sod-Plants
| 3000-12 | Fencing
| 3000-13 | Pool / SPA
| 3000-14 | (your description)
| 3000-15 | (your description)
|  | Total Yard-Landscape |  | 0 |  | 0
Foundation
| 4000-1 | PreTreat
| 4000-2 | Excavation & Backfill
| 4000-3 | Footings*
| 4000-4 | Foundation * (Basement/Stem Walls)
| 4000-5 | Slab (Form/Place/Finish)
| 4000-6 | Slab Leveling
| 4000-7 | Basement wall repairs/waterproofing
| 4000-8 | CMU/ Stemwall Repairs
| 4000-9 | Vapor Barrier (Crawl Space)
| 4000-10 | (your description)
| 4000-11 | (your description)
|  | Total Foundation |  | 0 |  | 0
Structure
| 5000-1 | Framing *(L & M)
| 5000-2 | Roof Trusses
| 5000-3 | Joist System
| 5000-4 | Stairs
| 5000-5 | Window (L & M)
| 5000-6 | Ext Doors (Main,access..)
| 5000-7 | Wall / Roof Sheathing Repairs
| 5000-8 | House Wrap
| 5000-9 | (your description)
| 5000-10 | (your description)
| 5000-11 | (your description)
|  | Total Structure |  | 0 |  | 0
Exterior
| 6000-1 | Roofing*
| 6000-2 | Flashing / Roof Repairs
| 6000-3 | Soffit / Fascia
| 6000-4 | Siding
| 6000-5 | Stucco
| 6000-6 | Masonry Veneer (Stone/Brick)
| 6000-7 | Decks
| 6000-8 | Painting - Exterior
| 6000-9 | Garage Door
| 6000-10 | Porch Repairs (Railing, columns..)
| 6000-11 | Gutters / Gutter Repairs (Cleaning)
| 6000-12 | Solar
| 6000-13 | (your description)
| 6000-14 | (your description)
| 6000-15 | (your description)
|  | Total Exterior |  | 0 |  | 0
Systems
| 7000-1 | Rough HVAC* (Ductwork)
| 7000-2 | Final HVAC (Start-up / Service)
| 7000-3 | (your description)
| 7000-4 | Underslab Plumbing (Rough)
| 7000-5 | Rough Plumbing (Top Out)
| 7000-6 | Plumbing - Fixtures
| 7000-7 | (your description)
| 7000-8 | Water Heaters
| 7000-9 | Fire Sprinklers Rough
| 7000-10 | Fire Sprinklers Final
| 7000-11 | Gas Rough
| 7000-12 | Gas Final
| 7000-13 | Underslab Electrical
| 7000-14 | Rough Electrical*
| 7000-15 | Electrical Fixtures / Lighting
| 7000-16 | Smoke / CO2 Detectors
| 7000-17 | (your description)
| 7000-18 | Low Voltage Rough
| 7000-19 | Low Voltage Final
| 7000-20 | (your description)
|  | Total Systems |  | 0 |  | 0
Interior
| 8000-1 | Insulation ( Batt & Blown)
| 8000-2 | Drywall
| 8000-3 | Painting - Interior
| 8000-4 | Fireplace
| 8000-5 | Fireplace Surrounds
| 8000-6 | Re-Surface Tubs / Re-glaze
| 8000-7 | (your description)
| 8000-8 | (your description)
|  | Total Interior |  | 0 |  | 0
Finishes
| 9000-1 | Finish Carpentry (Base,Case,Crown,Chair)
| 9000-2 | Interior Doors ( Pre-Hungs, Slabs..)
| 9000-3 | Finish Hardware (Door Knobs, Locks)
| 9000-4 | Cabinets (Kitchen & Bath)
| 9000-5 | Countertops (Kitchen & Bath)
| 9000-6 | Cabinet Re-finishing (paint, doors, re-skin)
| 9000-7 | Cabinet Hardware (New or replacement)
| 9000-8 | Mirrors
| 9000-9 | Shower Enclosures
| 9000-10 | Bath Accessories (Towel bars, TP MC)
| 9000-11 | (your description)
|  | Total Finishes |  | 0 |  | 0
Flooring
| 10000-1 | Tile / Marble
| 10000-2 | Wood Flooring (HW,Engineered,Laminate)
| 10000-3 | Refinish Hardwoods (repairs/fill in)
| 10000-4 | LVP (Vinyl Plank Flooring)
| 10000-5 | Carpet
| 10000-6 | Vinyl (Sheets,Linoleum)
| 10000-7 | Shoe Molding
| 10000-8 | Bath Tile (Tub/shower walls,pans,floors)
| 10000-9 | Backer Board (cement, dura-rock,Wonderboard)
| 10000-10 | Sub-floor / Sub floor repairs /leveling
| 10000-11 | (your description)
| 10000-12 | (your description)
|  | Total Flooring |  | 0 |  | 0
Appliances
| 11000-1 | Range
| 11000-2 | Cooktop
| 11000-3 | Microwave
| 11000-4 | Dishwasher
| 11000-5 | Refrigerator
| 11000-6 | Exhaust Hood
| 11000-7 | Total Appliance Package
| 11000-8 | Washer & Dryer (incl hoses,duct,connection)
| 11000-9 | Other Appliances (Wine, Ice, Trash Compactor)
| 11000-10 | (your description)
|  | Total Appliances |  | 0 |  | 0
Final - Misc
| 12000-1 | Cleaning ( roughs,Final,touchup)
| 12000-2 | Pressure Wash
| 12000-3 | Punch Kit (Misc., bulbs,batteries…)
| 12000-4 | MailBox & House #
| 12000-5 | (your description)
| 12000-6 | (your description)
|  | Total Misc. |  | 0 |  | 0
Other
| 13000-1 | Staging
| 13000-2 | Contingency
| 13000-3 | Overhead (released as a % of completion)
| 13000-4 | Profit (released as a % of completion)
| 13000-5 | (your description)
|  | Total Other |  | 0 |  | 0
*THESE ITEMS REQUIRE PERMITS IN MOST JURISDICTIONS. BORROWERS ARE REQUIRED TO ADHERE TO ALL LOCAL LAWS, CODES, REGULATIONS AND REQUIREMENTS AS EXPRESSED IN YOUR LOAN DOCUMENTS.

## Budget Example
v.
Construction Budget Submission Form
V | 5.1
Step 1: Fill out a description of the entire construction project.
Scope of Work: |  |  | Start Date: | 2023-05-01 | Total Budget:
The property is located in Greenville, SC and will be a complete gut and flip. We will demo all the drywall, current flooring, bathrooms, cabinets, countertops, roofing and back deck. We will be updating all HVAC and electrical and replacing all plumbing and electrical fixtures throughout. We will replace the roof with new shingles and construct a new deck on the back of the house. We will put new hardwood floors througout all living spaces, except the bathrooms which will have all new tile flooring and tile in the showers. The windows will also be replaced and new paint on the exterior and throughout the interior of the property. |  |  | Estimated Completion Date: | 2023-12-01 | 114300
|  |  | Expected Draws: | 6
|  |  |  | Current | Projected
|  |  | Total Square Feet: | 1563 | 1563
|  |  | Rooms/Units: | 7 | 7
|  |  | Bedrooms: | 3 | 3
|  |  | Bathrooms: | 2 | 2
|  |  | Kitchens: | 1 | 1
| Property Address: |  | Contractor: |  | Contact: |  |  |  |  | =IF(AMT_Recommend1="","",AMT_Recommend1)
| 123 Main Street, Greenville, SC 29601 | [8 empty] | =IF(FR_Comments="","",FR_Comments)
phone #
Step 2: Fill in each line item with the description of the construction cost, the amount, the estimated date of completion, and the draw item name (if necessary). By filling out this budget template, you acknowledge and understand that draws operate on a reimbursement model, and funds will be released post-close for completed work only.
Lima One Capital Budget Review
| Item Number | Category / Draw Item | Description | Amount | Comments |  | Recommended Budget | Comments
Soft Costs
| Item Number | Category / Draw Item | Description | Amount | Estimated Completion Date | Column6
| 1000-1 | Gas* Service / meter set
| 1000-2 | Water Service/Meter Set
| 1000-3 | Temp Power*/service / meter set
| 1000-4 | Temp Toilet
| 1000-5 | Architecutral Fees
| 1000-6 | Engineering Fees
| 1000-7 | Building Permit* | HVAC, electrical, plumbing and roofing permits | 1000 |  | 1000
| 1000-8 | Impact Fees
| 1000-9 | Survey/Drawings/Plans*
| 1000-10 | SWPP/ Erosion Control - Silt Fence
| 1000-11 | Temp Security / Privacy Fencing
| 1000-12 | (your description)
| 1000-13 | (your description)
|  | Total Soft Costs |  | 1000 |  | 1000
Demolition- Trashout
| 2000-1 | Demolition* | Demo all drywall, flooring, cabinets, fixtures, shingles and deck | 2300 |  | 2300
| 2000-2 | Trashout
| 2000-3 | Dumpster | Rental for construction debris removal | 1000 |  | 1000
| 2000-4 | HazMat Testing & Abatement
| 2000-5 | Mold Remediation
| 2000-6 | (your description)
| 2000-7 | (your description)
|  | Total Trashout |  | 3300 |  | 3300
Site Work
| 3000-1 | Grading*
| 3000-2 | Conduit / Electric Service
| 3000-3 | Water Lines*
| 3000-4 | Well
| 3000-5 | Septic *
| 3000-6 | Sewer Lines*
| 3000-7 | Flatwork -Conc Drive & Sidewalks
| 3000-8 | Asphalt
| 3000-9 | Pavers-Hardscape
| 3000-10 | Landscape (Package or Maintenance)
| 3000-11 | Sod-Plants
| 3000-12 | Fencing
| 3000-13 | Pool / SPA
| 3000-14 | (your description)
| 3000-15 | (your description)
|  | Total Yard-Landscape |  | 0 |  | 0
Foundation
| 4000-1 | PreTreat
| 4000-2 | Excavation & Backfill
| 4000-3 | Footings*
| 4000-4 | Foundation * (Basement/Stem Walls)
| 4000-5 | Slab (Form/Place/Finish)
| 4000-6 | Slab Leveling
| 4000-7 | Basement wall repairs/waterproofing
| 4000-8 | CMU/ Stemwall Repairs
| 4000-9 | Vapor Barrier (Crawl Space)
| 4000-10 | (your description)
| 4000-11 | (your description)
|  | Total Foundation |  | 0 |  | 0
Structure
| 5000-1 | Framing *(L & M)
| 5000-2 | Roof Trusses
| 5000-3 | Joist System
| 5000-4 | Stairs
| 5000-5 | Window (L & M) | Replace all windows with new black double pane, 10 windows | 5000 |  | 5000
| 5000-6 | Ext Doors (Main,access..)
| 5000-7 | Wall / Roof Sheathing Repairs
| 5000-8 | House Wrap
| 5000-9 | (your description)
| 5000-10 | (your description)
| 5000-11 | (your description)
|  | Total Structure |  | 5000 |  | 5000
Exterior
| 6000-1 | Roofing* | New roof with asphalt shingles | 12500 |  | 12500
| 6000-2 | Flashing / Roof Repairs
| 6000-3 | Soffit / Fascia | Repair soffit/fascia where needed after roof install | 1200 |  | 1200
| 6000-4 | Siding
| 6000-5 | Stucco
| 6000-6 | Masonry Veneer (Stone/Brick)
| 6000-7 | Decks | Build new 10x12 deck on back of house | 7800 |  | 7800
| 6000-8 | Painting - Exterior | Paint full exterior including all trim work | 5300 |  | 5300
| 6000-9 | Garage Door
| 6000-10 | Porch Repairs (Railing, columns..)
| 6000-11 | Gutters / Gutter Repairs (Cleaning)
| 6000-12 | Solar
| 6000-13 | (your description)
| 6000-14 | (your description)
| 6000-15 | (your description)
|  | Total Exterior |  | 26800 |  | 26800
Systems
| 7000-1 | Rough HVAC* (Ductwork) | Install new ductwork throughout | 4800 |  | 4800
| 7000-2 | Final HVAC (Start-up / Service) | Install new AC unit and furnace | 6200 |  | 6200
| 7000-3 | (your description)
| 7000-4 | Underslab Plumbing (Rough)
| 7000-5 | Rough Plumbing (Top Out)
| 7000-6 | Plumbing - Fixtures | Replace all bathroom and kitchen fixtures, new sinks, new toilets and vanities | 4600 |  | 4600
| 7000-7 | (your description)
| 7000-8 | Water Heaters
| 7000-9 | Fire Sprinklers Rough
| 7000-10 | Fire Sprinklers Final
| 7000-11 | Gas Rough
| 7000-12 | Gas Final
| 7000-13 | Underslab Electrical
| 7000-14 | Rough Electrical* | Update current fuse panel with 200 amp panel | 3800 |  | 3800
| 7000-15 | Electrical Fixtures / Lighting | Replace all electrical fixtures throughout and add recessed lighting in kitchen and living area | 3200 |  | 3200
| 7000-16 | Smoke / CO2 Detectors
| 7000-17 | (your description)
| 7000-18 | Low Voltage Rough
| 7000-19 | Low Voltage Final
| 7000-20 | (your description)
|  | Total Systems |  | 22600 |  | 22600
Interior
| 8000-1 | Insulation ( Batt & Blown)
| 8000-2 | Drywall | All new drywall througout | 5200 |  | 5200
| 8000-3 | Painting - Interior | All new paint throughout including trim | 6500 |  | 6500
| 8000-4 | Fireplace
| 8000-5 | Fireplace Surrounds
| 8000-6 | Re-Surface Tubs / Re-glaze
| 8000-7 | (your description)
| 8000-8 | (your description)
|  | Total Interior |  | 11700 |  | 11700
Finishes
| 9000-1 | Finish Carpentry (Base,Case,Crown,Chair) | New trim and baseboards throughout | 3400 |  | 3400
| 9000-2 | Interior Doors ( Pre-Hungs, Slabs..) | Install 10 new 6-panel doors | 2800 |  | 2800
| 9000-3 | Finish Hardware (Door Knobs, Locks) | New door knobs and cabinet pulls | 1200 |  | 1200
| 9000-4 | Cabinets (Kitchen & Bath) | Install new white shaker cabinets in kitchen | 7500 |  | 7500
| 9000-5 | Countertops (Kitchen & Bath) | Install new quartz countertops in kitchen | 5800 |  | 5800
| 9000-6 | Cabinet Re-finishing (paint, doors, re-skin)
| 9000-7 | Cabinet Hardware (New or replacement)
| 9000-8 | Mirrors
| 9000-9 | Shower Enclosures | Install new shower glass doors in both bathrooms | 2200 |  | 2200
| 9000-10 | Bath Accessories (Towel bars, TP MC)
| 9000-11 | (your description)
|  | Total Finishes |  | 22900 |  | 22900
Flooring
| 10000-1 | Tile / Marble | Install new tile flooring in both bathrooms and laundry room | 4200 |  | 4200
| 10000-2 | Wood Flooring (HW,Engineered,Laminate) | Install new hardwood floors througout, except bathrooms | 8600 |  | 8600
| 10000-3 | Refinish Hardwoods (repairs/fill in)
| 10000-4 | LVP (Vinyl Plank Flooring)
| 10000-5 | Carpet
| 10000-6 | Vinyl (Sheets,Linoleum)
| 10000-7 | Shoe Molding
| 10000-8 | Bath Tile (Tub/shower walls,pans,floors) | Install new tile walls in master shower | 2800 |  | 2800
| 10000-9 | Backer Board (cement, dura-rock,Wonderboard)
| 10000-10 | Sub-floor / Sub floor repairs /leveling
| 10000-11 | (your description)
| 10000-12 | (your description)
|  | Total Flooring |  | 15600 |  | 15600
Appliances
| 11000-1 | Range
| 11000-2 | Cooktop
| 11000-3 | Microwave
| 11000-4 | Dishwasher
| 11000-5 | Refrigerator
| 11000-6 | Exhaust Hood
| 11000-7 | Total Appliance Package
| 11000-8 | Washer & Dryer (incl hoses,duct,connection)
| 11000-9 | Other Appliances (Wine, Ice, Trash Compactor)
| 11000-10 | (your description)
|  | Total Appliances |  | 0 |  | 0
Final - Misc
| 12000-1 | Cleaning ( roughs,Final,touchup)
| 12000-2 | Pressure Wash
| 12000-3 | Punch Kit (Misc., bulbs,batteries…)
| 12000-4 | MailBox & House #
| 12000-5 | (your description)
| 12000-6 | (your description)
|  | Total Misc. |  | 0 |  | 0
Other
| 13000-1 | Staging
| 13000-2 | Contingency | For any overages | 5400 |  | 5400
| 13000-3 | Overhead (released as a % of completion)
| 13000-4 | Profit (released as a % of completion)
| 13000-5 | (your description)
|  | Total Other |  | 5400 |  | 5400
*THESE ITEMS REQUIRE PERMITS IN MOST JURISDICTIONS. BORROWERS ARE REQUIRED TO ADHERE TO ALL LOCAL LAWS, CODES, REGULATIONS AND REQUIREMENTS AS EXPRESSED IN YOUR LOAN DOCUMENTS.
Example
Example
Example
Example

## Reference (hidden)
Approvals:
1 | FALSE | FALSE | FALSE
2 | FALSE | FALSE | FALSE
3 | FALSE | FALSE | FALSE
4 | FALSE | FALSE | FALSE
RF_CountApprovals | 0
RF_Status | Initial Budget
RF_Analyst
RF_Date_Approved
Imported (boolean) | 0